## Sheet1
Name | Cost(days) | Progress | Remaining Days | Area | Area2 | Description
test4 | test4 | test4 | test4 | test4 | test4 | test4
Alex | 2 | 100 | 0 | Documents | WBS | Automated WBS entry. Created a microsoft form that automatically is added to an excel document.
Nikolai | 1 | 90% | 1 | Beta | Collecting Features | Collecting all features for the beta into one spot before integration
Gabriel | 1 | 100% | 0 | Player Controls & UI | Custom pick up item and swap item button | Created buttons for pick up item and swap item on options menu. Added to script but doesn't save keybinds separately.
Gabriel | 3 | 100% | 0 | Player Controls & UI | Saving multiple keybinds in PlayerPrefs. | Edited script to have separate strings in PlayerPrefs for each of the three keybinds.
Ben | 1 | 100% | 0 | GUI | Quest System | Added basic quest functions, requirements for the quests, steps to complete the quest, and rewards. Quest will be marked as finished when completed.
Gabriel | 3 | 100% | 0 | Player Controls & UI | Player controls using custom keybinds | Implemented custom keybinds into playercontroller script. Doesn't work because it doesn't recognize string names of keybinds stored in PlayerPrefs.
Gabriel | 2 | 100% | 0 | Player Controls & UI | Saving keybinds as ints | Saved keybinds as ints in PlayerPrefs because formatting doesn't get messed up and Input.GetKeyDown can recognize ints as input. Now displays ints instead of names of keys in options menu.
Nikolai | 1 | 100% | 0 | Demo | Demo | Demo
Nikolai | 1 | 50% | 0.5 | Generation |  | Getting rid of rotated tiles which ruin cohesion of room connections
Nikolai | 0.5 | 100% | 0 | Generation |  | Fixed bug that made enemy spawning not function
Jack N | 1 | 100% | 0 | Projectiles |  | Fixed projectiles clipping through walls and weapons having a delay when first spawned
Alex Knotwell | 3 | 30% | 2 | Animations |  | Created base with hell theme.
Jack N | 1 | 100% | 0 | Weapons |  | Enemies are now pushed back by knockback (set in projectile), depending on the enemy's resistance to knockback
Gabriel | 1 | 100% | 0 | UI |  | Made pause menu canvas. Has quit, resume and options buttons. pressing escape pauses game and opens pause menu. Can unpause game with resume or pressing escape again.
Alex | 1 | 6600% | 1 | Sentry Turret |  | Added animated fire on top of pedestal.
Jack N | 2 | 50% | 1 | Enemies |  | Tweaked shooter enemies so that they no longer move while firing. Going to try to see if I can make them space out a bit so they don't cluster.
Nikolai | 0.5 | 100% | 0 | Beta |  | Integrating Domingo's UI into current Beta
Nikolai | 0.5 | 10000% | 0 | UI |  | Added a minimap that allows the player to view their location in the dungeon
Gabriel | 1 | 100% | 0 | UI |  | Added options menu in pause menu with same functionality as main menu options menu. Only close button works right now working on keybinds and volume slider.
Gabriel | 1 | 100% | 0 | UI |  | Added functional keybinds and volume slider in options menu. Fixed bugs so pause is fully functional..
Nikolai | 1 | 100% | 0 | Spawning |  | Targets appear where enemies are going to spawn for a couple of seconds
Nikolai | 0.05 | 100% | 0 | Consumables |  | Heals a heart when drunk
Jack N | 1 | 100% | 0 | Enemies |  | Weaker fodder enemy to supplement the stronger ones
Nikolai | 0.5 | 100% | 0 | UI |  | Integrating pause menu into current beta
Jack N | 1 | 10000% | 0 | Room Generation |  | Added T room and Z room
Alex Knotwell | 1 | 80% | 1 | Sprites
Nikolai | 7 | 100% | 0 | Bugs |  | Tons of minor fixes
Nikolai | 0.25 | 100% | 0 | UI |  | Added icons to certain rooms on the minimap to make differentiating them easier
Nikolai | 1 | 100% | 0 | Game |  | Playtesting and debugging
Nikolai Repin | 0.5 | 100% | 0 | Journal |  | added journal to beta and put page item as a boss drop
Nikolai | 0.25 | 100% | 0 | Generation |  | increased and made more consistent rates for bonus rooms
Alex | 1 | 1000% | 3 | Sprites
Alex | 1 | 10000% | 0 | Beta
Alex | 2 | 5000% | 1 | Beta Testing
Alex | 7 | 1000% | 6 | Enemy |  | May not finish in time for final project review
test | test | test | test | test |  | test
Ben | 2 | 100% | 0 | Quest System |  | Added an NPC that you could interact with.
Ben | 3 | 8000% | 2 | Quest System |  | Added a Quest Window UI where it would display all current quests.
Ben | 2 | 10000% | 0 | UI |  | Added a Item Description UI on the side of the inventory to show details of an item when selected in the inventory.
Gabriel | 1 | 100% | 0 | Sprites |  | Made sprite changing screen. Has left, right, start and close buttons.
Ben | 1 | 10000% | 0 | UI |  | Cleaned up the Inventory UI to look neater and more functional
Gabriel | 1 | 100% | 0 | Sprites |  | Coded script to switch between sprites with left and right arrow.
Ben | 3 | 10000% | 0 | Quest System |  | Added a dialogue system anything could talk to you.
Ben | 1 | 10000% | 0 | Inventory |  | Added item data where you could easily change the name, icon, and description of an item in the Item Manager.
Gabriel | 1 | 100% | 0 | Sprites |  | Alternate skins can now be played with in game.
Nikolai | 0.25 | 100% | 0 | Generation |  | Added garuanteed bonus rooms
Nikolai | 1 | 100% | 0 | Weapons |  | Created weapon variation that charges up
Alexander | 3 | 100% | 0 | Art/Design |  | They look cool, it just adds a design and style element to the otherwise bland and blank enemies
Nikolai | 0.5 | 100% | 0 | Weapons |  | Added clips to player weapons that allow the firing of multiple bullets
Nikolai | 0.5 | 100% | 0 | Weapons |  | Created 3 new weapons for game including new charge and clip variations
Nikolai | 1 | 100% | 0 | Asthetics |  | Made each dungeon floor have different colors
Ben | 1 | 100% | 0 | Items |  | Integrated other existing items to work be able to be picked up and shown in the inventory.
Nikolai | 1 | 100% | 0 | Journal |  | Fixed bugs with page items and loading pages when opening journal
Nikolai | 1 | 100% | 0 | Weapons |  | Fixed bug with clip weapons firing at different speed on different frame rates
Nikolai | 0.1 | 100% | 0 | Generation |  | Decreased loading times
Nikolai | 1 | 100% | 0 | Items |  | Added item that heals the player
Nikolai Repin | 1 | 100% | 0 | Balancing |  | Made going through portals heal the player and added a chance to drop heal items upon room clear
Ben | 7 | 10000% | 0 | Bugs |  | Fixed lots of minor and major bugs in the Inventory System
Jack N. | 7 | 10000% | 0 | Enemies
Jack N. | 3 | 10000% | 0 | Enemies
Jack N | 3 | 10000% | 0 | Room Generation
Nikolai | 1 | 100% | 0 | Items |  | Healing when finishing a floor and occasional health drops upon clear
Alex Knotwell | 1 | 10000% | 0 | Main Menu |  | Fixed bugged Skin Selection screen
Alex Knotwell | 1 | 10000% | 0 | Building Game |  | Skin Selector script had editor-only code that stopped the game from being built, wrote a work around to that.