## Sheet1
Owner | Cost(days) | Progress | Remaining Days | Area | Feature | Description
Jack Nieman | 1 | 10 | 15 | Enemies | Demo Boss | Added a boss with difficult yet fun attack patterns, with everything for the next area loading showing up afterwards
Jack Nieman | 2 | 20 | 13 | Weapons | Firing and rotation
Jack Nieman | 2 | 30 | 11 | Weapons | Fixing rotation, adding customizable projectiles
Jack Nieman | 2 | 40 | 9 | Weapons | Fixed merge conflicts, implementing mana
Jack Nieman | 2 | 55 | 7 | Weapons | Implementing random stats
Jack Nieman | 2 | 70 | 5 | Weapons | Picking up weapons
Jack Nieman | 2 | 85 | 3 | Weapons | Dropping weapons
Jack Nieman | 2 | 90 | 1 | Weapons | More work on debugging weapons
Ben | 1 | 100% | 0 | UI | Inventory Design | Designed an inventory layout that can be opened and close with TAB.
Ben | 1 | 100% | 0 | UI | Toolbar Design | Designed a toolbar, changed from 5 slots to 2 slots, can switch from slot to slot.
Ben | 1 | 100% | 0 | UI | Item Pickup for Inventory | Added pick up items when player collided with an object, allowed for the item to go into the inventory with a max stack of 10.
Ben | 1 | 100% | 0 | UI | Collectables and Items | Created an easy way for items or collectables to be sorted and categorized. Allows for easier item management. Refactored items.
Ben | 1 | 100% | 0 | UI | Dropping items from Inventory | Added drop button for dropping items from inventory, items would drop around the player randomly so that player wouldn’t collect item immediately after dropped.
Ben | 1 | 100% | 0 | UI | Drag and dropping items in inventory | Items can be dragged around the screen; however, it doesn’t get dropped from the inventory onto the canvas.
Ben | 1 | 100% | 0 | UI | Remove Item Canvas | Added remove item canvas where when items are dragged onto the canvas and dropped, it will be dropped onto the scene and removed from the inventory, can be re picked up. If LSHIFT is held when dropping, only one item is dropped.
Ben | 1 | 100% | 0 | UI | Game Manager and UI Manager | Made it easier to setup more inventories or change layout and slots. Inventory is changed to “backpack.”
Ben | 1 | 100% | 0 | UI | Moving items | Allows items to be moved to different slots in the inventory by dragging and dropping. Slot will then contain that item and when items are picked up, it goes into that slot.
Domingo | 4 | 90% | 1 | GUI | Visual display for health and mana | Added UI for health and mana that updates itself when needed.
UI scales with screen size.
Domingo | 3 | 100% | 0 | Gameplay | Added items that an affect player’s stats | Item that increases damage by a specified amount. Bullet size will scale with damage.
Item that increases speed. Dash strength scales with speed
Item that changes the rate at which you gain mana, as well as your max mana
Item that changes and updates max health.
Nikolai | 1 | 100% | 0 | Pathfinding | Create basic enemy with simple pathfinding | Learning use of pathfinding package
Create very barebones enemy AI
Nikolai | 1 | 100% | 0 | Pathfinding | Add different ai types | Add ranged AI type
Add melee AI type
Nikolai | 1 | 100% | 0 | Room Generation | Room Alignment | Modify rooms to include door information for alignment
Framework
Nikolai | 2 | 100% | 0 | Room Generation | Room Alignment | Create function that aligns two rooms door to door
Nikolai | 1 | 100% | 0 | Room Generation | Implement hallway placement | Add option for hallways to connect two rooms together
Alex | 3 | 100% | 0 | Room Prefabs | Base rooms for dungeon gen | Create base room layouts and hallways that are to be used and implemented in room generation
Alex | 3 | 10% | 5 | Story | Story journal & pick ups | Create items that can be picked up to add content to a journal that holds a small story element.
Nikolai | 2 | 100% | 0 | Room Generation | Create basic generation algorithm | Creates a main branch from start to finish.
Creates off shoot branches.
Nikolai | 1 | 100% | 0 | Room Generation | Convert generation algorithm to coroutine setup
Alex Knotwell | 2 | 100% | 0 | Github | Repository Set-Up | Set-up repository with Unity .gitignore file
Alex Knotwell | 2 | 100% | 0 | Github | Onboarding | Onboarded all members onto the repo and taught them baisc commands
Alex Knotwell | 1 | 100% | 0 | Sprites | Testing | Added sprites and tileset we can use for testing.
Alex Knotwell | 2 | 50% | 2 | Enemies | Enemy health | Added a C# script that caused enemies to take damage from player's bullet.
Alex Knotwell | 2 | 100% | 0 | Enemies | Enemy health | Added a health bar that would decrease by 20% on each hit. Game ends when health is 0.
Alex Knotwell | 1 | 100% | 0 | Enemies | Enemy health | Fixed enemy health to work with updated bullet script.
Alex Knotwell | 1 | 100% |  | Enemy Animation | Enemy animation set up | Added Input System package and created folder for Angry Slime animations
Alex Knotwell | 2 | 25% | 10 | Enemy Animation | Left/Right movement | Created movement animations for the Angry Slime.
Alex Knotwell | 2 | 50% | 8 | Enemy Animation | Up/Down movement | Created up/down movement for Angry slime.
Alex Knotwell | 3 | 75% | 5 | Enemy Animation | Animation | Setting up all animations in Unity in the animator and be able to be called in a script.
Alex Knotwell | 5 | 100% | 0 | Enemy Animation | Integrating animation | Created script that calls correct animations when A* Pathfinding changes movement. Also has death animation when health is 0.
Alex Knotwell | 5 | 50% | 2 | Player Animation | Walking left/right. | Created 2 7 frame animations for player to walk left or right.
Gabriel | 1 | 100% | 0 | Sprites & Textures | Research | Online research for texture pack
Gabriel | 1 | 100% | 0 | Sprites & textures | Import sprite package | Imported package with sprites and tiles
Gabriel | 1 | 100% | 0 | Sprites & Textures | Tile pallet & sample room | Made tile pallet from package and sample room using tiles all in map scene
Gabriel | 1 | 100% | 0 | UI | Title screen | Made title screen canvas from imported UIiset. Has generic game title with custom font
Gabriel | 1 | 100% | 0 | UI | Title screen buttons | Non-functional start, quit, and options buttons. Buttons change appearance when pressed.
Gabriel | 1 | 100% | 0 | UI | Start button | Wrote script for Start button which switches to main game scene
Gabriel | 1 | 100% | 0 | UI | Quit button | Wrote script for quit button which quits application. I haven’t tested because I need to build the game on desktop to test quit.
Gabriel | 1 | 100% | 0 | UI | Options Menu and volume slider | Created options menu canvas with generic non-functional volume slider
Gabriel | 1 | 100% | 0 | UI | Volume value & close button | Text shows numerical value of volume. The close button makes the options menu invisible.
Gabriel | 1 | 100% | 0 | UI | Volume slider functional | The volume slider is connected to game audio. I have not tested it because there is no music yet.
Gabriel | 1 | 100% | 0 | Player Controls & UI | Custom attack keybind button | Made button in options menu for attack keybinds. Wrote script to show custom keybinds on button and store in PlayerPrefs as a string. Saves keybinds even after closing game.
Jack Nieman | 3 | 100% |  | Game Manager | Portal to Next Level